Cuckney Holbeck Welbeck and Norton Neighbourhood planning meeting

At Welbeck Club 8th June 2015

Present

Natalie Cockrell, David Collins, David Wall, Mike Smith, Caroline Chambers

Georgina Smith, Darren Ridout, Keith Barlow, Claire Barlow, Richard Bower

Sheila Brailsford, James Green

1. Welcome – All members of the steering group were present, and we had a group photo taken for the final document
2. Updates on progress towards the consultation commencing on 15th June
* JG – I have been working on formatting version 6. If there are any minor changes, they can be done later. Pictures are needed later but at present it makes it too slow on the computer

DC – we need random photos through the document. Please proof read and all changes to be sent to JG by 5pm on Wed.

GS- Project 10 – send to JG

KB- Project 2 – does it need to be more definite?

NC- No. the vaguer they are, the easier to work out later.

Executive summary

DC – The executive summary needs to be A5.

The detail of the summary was discussed

CC – What about Tourism and job opportunities?

MS- Policy 3 – should read to buy and to let

DC – 1000 copies of the Executive summary and 20 copies of the Draft Neighbourhood plan. We’ll leave copies of the NP at Cuckney shop for people to take. The Latest version of the NP would also be available on the website. NC and JG to liaise with MS to upload documents to the website

The summaries would be delivered on Friday and steering group members arranged delivery to each household.

The Consultation Question sheet- NC to provide 30 feedback forms to be held at Cuckney shop. Anyone wishing to make comments has to use this form

Informing the public of the consultation period

NC- to put it on Bassetlaw website

GS – to email press detail to NC for Chad and Worksop Guardian

DC – To put in Parish newsletter

Practicalities

DC Boards will be prepared to use at various Festival events

to inform people about the Neighbourhood Plan.

A rota was arranged for steering group members to be responsible for setting up a stand at various events and handing it on to the next person.

Any other business

RB – RB and KB walked the footpaths along the dam meadow. The bridge is dangerous. The far end of the path is very swampy and it would not be suitable to change the existing footpath. As for a circular route – RB will ask Mr Spinks about it.

Re: Footpaths crossing Philip Willisons land – The possibility of a path off Old Mill lane up the river is problematic because of the swampy nature of the terrain.

Crossing the A616 at High Hadfield is dangerous and PW is not in favour of a route through Low Hadfield farm. But a circular route along the top of the fields and into the woods could be feasible.

JG: are all the green spaces agreed by the landowner?

DR: I am meeting with Mr Parente on 18th June as part of the consultation.

Meeting Closed

Date of next meeting not arranged